## Sheet1
Project name | Wind farm modelling project
Project sponsor | AN Author
Version number | 3
Date | 09/05/2011
|  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6
Task | Owner | Time | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Define problem | GH | 1
Identify outputs | GH | 0.5
Identify inputs | AS | 0.5
Check data availability | NH | 1
Review outputs and inputs | AS | 1
Describe input behaviours | GH | 1
Identify economic logic | GH | 2
Business model specified |  | 7
Data collection | NH | 16
Data collected |  | 16
Model construction | AS | 14
Model built |  | -
Data entry | AS | 1
Scenario testing | AS | 2
Report writing | GH | 2
Report presented |  | 5
Review project | GH | 1
Project reviewed |  | 1
Total project time |  | 29
Key
Task/activity
Milestone